## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US1 | Overview - The AI-Based Fraud Management System for UID Aadhaar is designed to detect and prevent fraudulent activities by analyzing Aadhaar data using advanced AI models. Its primary goals are to ensure data integrity, enhance security, and streamline the detection of anomalies through classification, detection, and OCR techniques. | MUST HAVE | NO | Mentor-521 | 3- Completed
S2 | S2 | US2 | Workflow - The system workflow begins with the classification model identifying a image is whether aadhar or non-aadhar. Next, the detection model Identifies and crops relevant sections (name, UID, address) from Aadhaar card images. The OCR model then extracts text and details from Aadhaar documents for further analysis. Finally, the results are evaluated against predefined business rules to compute a fraud score, determining if the input passes or flags as fraudulent. | SHOULD HAVE | NO | Mentor-521 | 3- Completed
S3 | S3 | US3 | Document Usecase - include detecting forged Aadhaar documents, mismatched data, and tampered biometrics. Resolution involves flagging issues, notifying authorities, and updating logs for investigation. | MUST HAVE | NO | Mentor-521 | 3- Completed
S4 | S4 | US4 | Knowedge of Models - Research and compile knowledge about the models used for classification, detection, and OCR processes. | SHOULD HAVE | Research Papers | Mentor-521 | 3- Completed
S5 | S5 | US5 | Classification Model - Develop the classification model for identifying a image is aadhar or non-aadhar using YOLO. | MUST HAVE | YOLO | Mentor-521 | 3- Completed
S6 | S6 | US6 | Detection Model - Identifies and crops relevant sections (name, UID, address) from Aadhaar card images. | MUST HAVE | YOLO | Mentor-521 | 3- Completed
S7 | S7 | US7 | OCR Model - Extracts text from the cropped sections using EasyOCR. | MUST HAVE | easyocr | Mentor-521 | 3- Completed
S8 | S8 | US8 | Backened - backend system for managing data and fraud detection logic using Flask. | MUST HAVE | Flask | Mentor-521 | 3- Completed
S9 | S9 | US9 | Frontened - frontend interface for the system using HTML, CSS for user interaction. | MUST HAVE | HTML, CSS | Mentor-521 | 3- Completed
S10 | S10 | US10 | Connecting Frontened and Backened - Integrate the frontend and backend using JavaScript for seamless communication between the two layers. | MUST HAVE | JavaScript | Mentor-521 | 3- Completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 62 | 15 | 14 | 11 | 9 | 4 | 4 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US1 | TID-01 | Overview of project | 2025-02-07 | 2025-02-08 | Aliya Rizvi | Others | 3- Completed | 5 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US2 | TID-02 | Workflow of the project | 2025-02-10 | 2025-02-11 | Aliya Rizvi | Design | 3- Completed | 8 | 2 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US3 | TID-03 | Document Usecase | 2025-02-12 | 2025-02-14 | Aliya Rizvi | Others | 3- Completed | 5 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US4 | TID-04 | Knowledge of Models | 2025-02-17 | 2025-02-17 | Aliya Rizvi | Others | 3- Completed | 10 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US5 | TID-05 | Classification Model | 2025-02-18 | 2025-02-18 | Aliya Rizvi | Coding | 3- Completed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US6 | TID-06 | Detection Model | 2025-02-19 | 2025-02-21 | Aliya Rizvi | Coding | 3- Completed | 8 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US7 | TID-07 | OCR Model | 2025-02-25 | 2025-02-27 | Aliya Rizvi | Coding | 3- Completed | 4 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US8 | TID-08 | Backend Model | 2025-02-28 | 2025-03-03 | Aliya Rizvi | Coding | 3- Completed | 12 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
US9 | TID-09 | Frontend Model | 2025-03-03 | 2025-03-04 | Aliya Rizvi | Coding | 3- Completed | 6 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US10 | TID-10 | Connecting Frontend and Backend | 2025-03-05 | 2025-03-07 | Aliya Rizvi | Coding | 3- Completed | 4 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
S1 | Day 2 | Lack of clarity of project description | Conducted a detailed discussion with mentor
S1 | Day 3 | Lack of clarity of project goals | Conducted a detailed discussion with mentor
S2 | Day 5 | Difficulty in understanding the workflow of the project | Understand Various AI Project workflow
S4 | Day 10 | Difficulty in understanding the models for the project | Conducted a detailed discussion with mentor
S6 | Day 12 | Error in detection model related to path | Discussed with mentor and got the solution
S7 | Day 18 | Difficulty in implementation of OCR model | Understood the concept of OCR using easyocr module
S8 | Day 21 | Difficulty in choosing the right technology for backend | Discussed with mentor and got the solution to use Flask
S10 | Day 34 | Confusion in connecting frontend and backend | Got the solution by discussing to the mentor by making the pipeline

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | S1 | 2025-02-07 | 2025-02-08 | Aliya Rizvi | Researching on the project | Assuming that it willl be an introduction and not much important | Taking meeting regularly | Ask my mentor to explain the project
2 | S2 | 2025-02-10 | 2025-02-11 | Aliya Rizvi | Understanding the various AI Project Workflows | Thinking that it is not important for project development | Discussing with the mentor to get clear understanding on the workflow | Ask my mentor to explain the project workflow
3 | S3 | 2025-02-12 | 2025-02-14 | Aliya Rizvi | research on the various use case of the project | Thinking that use case is not important | Taking meeting regularly | Uderstand the use case of the project
4 | S4 | 2025-02-17 | 2025-02-17 | Aliya Rizvi | Learning various models for image processing projects | Assuming that meeting is not important for completion of internship | Attend the meeting to get idea of different models in AI | Conducted a detailed discussion with mentor
5 | S5 | 2025-02-18 | 2025-02-18 | Aliya Rizvi | learning classification model for image classification | Stop doing implementation of the classification model without proper understanding | Learning about classification model | learn about classification model on internet and with the mentor
6 | S6 | 2025-02-19 | 2025-02-21 | Aliya Rizvi | implementing detection model to detect name,uid, and address | Stop assuming that it is not important for the project | implementing detection model using YOLO | Discussed with mentor and got the solution
7 | S7 | 2025-02-25 | 2025-02-27 | Aliya Rizvi | Building OCR model to extract content from the aadhaar image | Stop implementing the ocr model with other module than easyocr | implementing detection model using easyocr | Understood the concept of OCR using easyocr module